## Summary
KLIP v1: plan summary
Edit the blue cells on yellow. Everything else recalculates.
Inputs
Start date | 2026-10-12 | Assumption: the Monday after this plan was made
Live deadline | 2026-10-30 | Set by you: 30 Oct 2026
Local-working milestone | 2026-10-22 | Assumption: register, login and entries API work end to end
Hours per week available | 14 | Assumption: about 2h every day, no days off. Replace with your real number
Summary
Estimate, low (h) | 31.5
Estimate, mid (h) | 33.5 | Average of low and high per task
Estimate, high (h) | 35.5
Actual hours logged | 0
Hours remaining (not Done) | 31 | Mid estimate of tasks not marked Done
Days left to deadline | 18 | Counts from today's date
Hours/week needed to hit deadline | 12.0556 | Compare with your hours per week above
Projected finish at your pace | 2026-10-28
Verdict | On track
Tasks done | 2 of 12
Notes and assumptions
Colour key: blue text = input you edit; black = formula.
On Tasks, set Status from the dropdown (e.g. Done) and log Actual hours (e.g. 2.5).
Task estimates are mine: the rows sum to 31.5-35.5 h; the 30-40 h headline allowed for slack.
Not included: product photos (+1-2 days), phone OTP verification (+1-2 days), password reset, notifications.
Planned finish runs tasks in order at your weekly hours and ignores college deadlines or days off.

## Tasks
KLIP v1: task plan
Estimates are mine (low/high hours per task). Edit blue cells: Status and Actual hrs. Planned finish assumes tasks run in order at the hours/week set on the Summary sheet.
# | Phase | Task | Who writes it | Milestone | Low (h) | High (h) | Est. (h) | Status | Actual (h) | Cumulative (h) | Planned finish | Flag | Notes
1 | Backend | Test auth (5 cases), fix bugs, write phone.js, startup env check | You | Local | 2 | 2 | 2 | Done |  | 2 | 2026-10-13 | Done | Register, duplicate, login ok/wrong/unknown phone; one shared phone format
2 | Backend | requireAuth middleware | You | Local | 0.5 | 0.5 | 0.5 | Done |  | 2.5 | 2026-10-14 | Done | Bearer token, id from token only
3 | Backend | Entry endpoints: create, list, confirm/dispute, settle | You | Local | 5 | 7 | 6 | Not started |  | 8.5 | 2026-10-17 | On track | Each change + entry_events row in one transaction; ownership in the WHERE clause
4 | Backend | Error handler and validation cleanup | Both | Local | 1 | 1 | 1 | Not started |  | 9.5 | 2026-10-17 | On track
5 | Frontend | Vite + React scaffold, routing, API client, auth state | Claude | Live | 3 | 3 | 3 | Not started |  | 12.5 | 2026-10-19 | On track | Plain SPA, thin client; no business logic
6 | Frontend | Login and register pages | Both | Live | 2 | 2 | 2 | Not started |  | 14.5 | 2026-10-20 | On track
7 | Frontend | Dashboard (owed to me / I owe) | Both | Live | 3 | 3 | 3 | Not started |  | 17.5 | 2026-10-21 | On track
8 | Frontend | Create-entry form | Both | Live | 2 | 2 | 2 | Not started |  | 19.5 | 2026-10-22 | On track
9 | Frontend | Entry detail with confirm / dispute / settle | Both | Live | 3 | 3 | 3 | Not started |  | 22.5 | 2026-10-24 | On track
10 | Frontend | Styling and mobile layout | Both | Live | 3 | 4 | 3.5 | Not started |  | 26 | 2026-10-25 | On track
11 | Launch | Deploy backend + frontend, CORS, trust proxy, production Neon branch | Both | Live | 3 | 4 | 3.5 | Not started |  | 29.5 | 2026-10-27 | On track | Expect surprises here
12 | Launch | End-to-end testing and bug fixing | You | Live | 4 | 4 | 4 | Not started |  | 33.5 | 2026-10-29 | On track
|  | Total |  |  | 31.5 | 35.5 | 33.5 |  | 0
Formulas:
Planned finish = Summary!$B5+ROUNDUP([Cumulative (h)]*7/Summary!$B8,0)